## List of all things to do
Learn Java | Game | GUI | AI | Networking
Do Report | Pieces | Changing Board Color | Timer for the AI | Create Socket
| Board | GUI board | Computer identifies valid moves | Implement Client Side
| Moving Pieces | Create spaces in the board | Computer can randomly select a valid move | Implement Server Side
| Making pieces not go in the opponents store | Create each user's store | Computer Looks ahead one move in tree | Bind Client and Server
| End Game Scenerios | label each space to help users move by typing | Computer can identify special moves (ex: moves that allow it to go again, moves that steal pieces)
| Count pieces in store | GUI Pieces | Create a utility function
| 2 Players | Clicking to move pieces | Evaluation Function to find perfect utilities
| Restart option | Typing to move pieces | Minimax tree used for AI
| quit option | Sound | Alpha-beta pruning implemented at one level
| Rule where piece in empty place steals opposite pieces | Numbers for each place | Alpha-beta pruning implemented at all levels
| Rule where when person has no pieces on their side, opposite gets all of their pieces, game ends | Scoreboard image | Iterative deepening implemented
| Last piece in your mancala and you get another turn | Instruction Page/Introduction Screen
| Scoreboard | Buttons for everyting
| Option to have timer | User response for invalid move
Show timer
Output victory/defeat message
Have others test the GUI, try to break it
Create spaces
Create Store

## Pre-Sprint 1 Overall Backlog
Task | Hours | Person
Learn Java | 5 | All
Pieces | 1 | Drew
Board | 1 | Drew
Create spaces | 1 | Drew
Create Store | 1 | Drew
Moving Pieces | 2 | Haaris
Making pieces not go in the opponents store | 0.5 | Haaris
End Game Scenerios | 1 | Haaris
Count pieces in store | 0.5 | Haaris
Restart option | 0.5 | Kraig
quit option | 0.5 | Kraig
Rule where piece in empty place steals opposite pieces | 2 | Kraig
Rule where when person has no pieces on their side, opposite gets all of their pieces, game ends | 2 | Kraig
Last piece in your store and you get another turn | 2 | Kraig
Scoreboard | 1 | Haaris
2 Players | 3 | Drew
Option to have timer | 2 | Kraig
GUI board | 3 | Haaris
Create spaces in the board | 1 | Haaris
Create each user's store | 1 | Haaris
label each space to help users move by typing | 1 | Haaris
GUI Pieces | 2 | Drew
Clicking to move pieces | 2 | Drew
Typing to move pieces | 2 | Drew
Scoreboard image | 1 | Kraig
Instruction Page/Introduction Screen | 1 | Kraig
Buttons for everyting | 1 | Kraig
User response for invalid move | 1 | Drew
Have others test the GUI, try to break it | 1 | All
Create Socket | 2 | Kraig
Implement Client Side | 2 | Haaris
Implement Server Side | 2 | Drew
Bind Client and Server | 2 | All
Timer for the AI | 1 | Kraig
Computer identifies valid moves | 1 | Drew
Computer can randomly select a valid move | 1 | Haaris
Computer Looks ahead one move in tree | 3 | Drew
Computer can identify special moves (ex: moves that allow it to go again, moves that steal pieces) | 2 | Kraig
Create a utility function | 5 | Haaris/Kraig
Evaluation Function to find perfect utilities | 1 | Haaris/Kraig
Minimax tree used for AI | 10 | Drew
Alpha-beta pruning implemented at one level | 3 | Haaris/Kraig
Alpha-beta pruning implemented at all levels | 2 | Haaris/Kraig
Iterative deepening implemented | 2 | Haaris/Kraig
Changing Board Color | 0.5 | Drew
Sound | 0.5 | Haaris
Numbers for each place | 0.5 | Kraig
Show timer | 0.5 | Kraig
Output victory/defeat message | 0.5 | Drew

## Sprint 1 Backlog
Task | Hours | Person
Learn Java | 5 | All
Pieces | 1 | Drew
Board | 1 | Drew
Create spaces | 1 | Drew
Create Store | 1 | Drew
Moving Pieces | 2 | Haaris
Making pieces not go in the opponents store | 0.5 | Haaris
End Game Scenerios | 1 | Haaris
Count pieces in store | 0.5 | Haaris
Restart option | 0.5 | Kraig
quit option | 0.5 | Kraig
Rule where piece in empty place steals opposite pieces | 2 | Kraig
Rule where when person has no pieces on their side, opposite gets all of their pieces, game ends | 2 | Kraig
Last piece in your store and you get another turn | 2 | Kraig
Scoreboard | 1 | Haaris
2 Players | 3 | Drew

## Post Sprint 1 Remaining Backlog
Task | Hours | Person
Rule where piece in empty place steals opposite pieces | 1 | Drew
Scoreboard | 1 | Haaris
2 Players | 2 | Haaris
Option to have timer | 1 | Drew
GUI Display Timer | 1 | Haaris
label each space to help users move by typing | 1 | Haaris
Typing to move pieces | 2 | Drew
Scoreboard image | 0.5 | Haaris
Instruction Page/Introduction Screen | 0.25 | Haaris
Buttons for everyting | 0.25 | Haaris
User response for invalid move | 0.5 | Haaris
Have others test the GUI, try to break it | 1 | Haaris
Create Socket | 2 | Kraig
Implement Client Side | 2 | Kraig
Implement Server Side | 2 | Kraig
Bind Client and Server | 2 | Kraig
Integrate Networking with the rest of the game | 5 | Kraig
Timer for the AI | 1 | Kraig
Computer identifies valid moves | 1 | Drew
Computer can randomly select a valid move | 1 | Haaris
Computer Looks ahead one move in tree | 3 | Drew
Computer can identify special moves (ex: moves that allow it to go again, moves that steal pieces) | 2 | Kraig
Create a utility function | 5 | Haaris/Kraig
Evaluation Function to find perfect utilities | 1 | Haaris/Kraig
Minimax tree used for AI | 10 | Drew
Alpha-beta pruning implemented at one level | 3 | Drew/Kraig
Alpha-beta pruning implemented at all levels | 2 | Haaris/Kraig
Iterative deepening implemented | 2 | Haaris/Kraig
Changing Board Color | 0.5 | Haaris
Sound | 0.5 | Haaris
Numbers for each place | 0.5 | Haaris
Show timer | 0.5 | Haaris
Output victory/defeat message | 0.5 | Haaris

## Sprint 2 Backlog
Task | Hours | Person
Rule where piece in empty place steals opposite pieces | 1 | Drew
Scoreboard | 1 | Haaris
2 Players | 2 | Haaris
Option to have timer | 1 | Drew
GUI Display Timer | 1 | Haaris
label each space to help users move by typing | 1 | Haaris
Typing to move pieces | 2 | Drew
Scoreboard image | 0.5 | Haaris
Instruction Page/Introduction Screen | 0.25 | Haaris
Buttons for everyting | 0.25 | Haaris
User response for invalid move | 0.5 | Haaris
Have others test the GUI, try to break it | 1 | Haaris
Create Socket | 2 | Kraig
Implement Client Side | 2 | Kraig
Implement Server Side | 2 | Kraig
Bind Client and Server | 2 | Kraig
Computer identifies valid moves | 1 | Drew
Computer can randomly select a valid move | 1 | Haaris

## Post Sprint 2 Remaining Backlog
Integrate Networking with the rest of the game | 5 | Kraig
Timer for the AI | 1 | Kraig
Computer Looks ahead one move in tree | 3 | Drew
Computer can identify special moves (ex: moves that allow it to go again, moves that steal pieces) | 2 | Kraig
Create a utility function | 5 | Haaris/Kraig
Evaluation Function to find perfect utilities | 1 | Haaris/Kraig
Minimax tree used for AI | 10 | Drew
Alpha-beta pruning implemented at one level | 3 | Drew/Kraig
Alpha-beta pruning implemented at all levels | 2 | Haaris/Kraig
Iterative deepening implemented | 2 | Haaris/Kraig
Changing Board Color | 0.5 | Haaris
Sound | 0.5 | Haaris
Numbers for each place | 0.5 | Haaris
Show timer | 0.5 | Haaris
Output victory/defeat message | 0.5 | Haaris

## Sprint 3 Backlog
Integrate Networking with the rest of the game | 5 | Kraig
Integrate Networking with the rest of the game | 3 | Haaris
Timer for the AI | 1 | Kraig
Computer Looks ahead one move in tree | 3 | Drew
Computer can identify special moves (ex: moves that allow it to go again, moves that steal pieces) | 2 | Kraig
Create a utility function | 2 | Drew/Kraig
Evaluation Function to find perfect utilities | 1 | Haaris/Kraig
Minimax tree used for AI | 10 | Drew
Alpha-beta pruning implemented at one level | 3 | Drew/Kraig
Alpha-beta pruning implemented at all levels | 2 | Haaris/Kraig
Iterative deepening implemented | 2 | Haaris/Kraig
Changing Board Color | 0.5 | Haaris
Sound | 0.5 | Haaris
Numbers for each place | 0.5 | Haaris
Show timer | 0.5 | Haaris
Output victory/defeat message | 0.5 | Haaris

## Burndown Chart
Date | Remaining Hours | Ideal Remaining Hours
2017-10-27 | 120.5 | 120.5
2017-10-29 | 98.5 | 112
2017-10-31 | 91.5 | 103.5
2017-11-03 | 89 | 100
2017-11-05 | 73 | 95
2017-11-08 | 65 | 77.5
2017-11-10 | 53 | 68.5
2017-11-12 | 49 | 59.5
2017-11-15 | 46 | 50.5
2017-11-16 |  | 42.5
2017-11-18 |  | 34.5
2017-11-20 |  | 26.5
2017-11-22 |  | 18.5
2017-11-24 |  | 10.5
2017-11-26 |  | 3
2017-11-28 |  | 0

## Haaris Burndown
Date | Other | Game | GUI | AI | Networking | Total
2017-10-27 | 6 | 6 | 8 | 18 | 5 | 43
2017-10-29 | 3 | 4 | 6 | 18 | 5 | 36
2017-10-31 | 2 | 4 | 4 | 18 | 5 | 33
2017-11-03 | 2 | 4 | 3 | 18 | 5 | 32
2017-11-05 | 1 | 0 | 10 | 11 | 0 | 22
2017-11-08 | 1 | 0 | 9 | 11 | 0 | 21
2017-11-10 | 1 | 0 | 2 | 11 | 0 | 14
2017-11-12 | 1 | 0 | 2 | 6 | 3 | 12
2017-11-15 | 1 | 0 | 2 | 6 | 2 | 11
2017-11-16 | [5 empty] | 0
2017-11-18 | [5 empty] | 0
2017-11-20 | [5 empty] | 0
2017-11-22 | [5 empty] | 0
2017-11-24 | [5 empty] | 0
2017-11-26 | [5 empty] | 0
2017-11-28 | [5 empty] | 0

## Drew Burndown
Date | Other | Game | GUI | AI | Networking | Total
2017-10-27 | 6 | 7 | 7 | 11 | 5 | 36
2017-10-29 | 3 | 4 | 6 | 11 | 5 | 29
2017-11-01 | 3 | 4 | 4 | 11 | 5 | 27
2017-11-03 | 3 | 4 | 3 | 11 | 5 | 26
2017-11-05 | 1 | 4 | 0 | 17 | 0 | 22
2017-11-08 | 1 | 4 | 0 | 17 | 0 | 22
2017-11-10 | 1 | 1 | 0 | 16 | 0 | 18
2017-11-12 | 1 | 1 | 0 | 17 | 0 | 19
2017-11-15 | 1 | 1 | 0 | 16 |  | 18
2017-11-16 | [5 empty] | 0
2017-11-18 | [5 empty] | 0
2017-11-20 | [5 empty] | 0
2017-11-22 | [5 empty] | 0
2017-11-24 | [5 empty] | 0
2017-11-26 | [5 empty] | 0
2017-11-28 | [5 empty] | 0

## Kraig Burndown
Date | Other | Game | GUI | AI | Networking | Total
2017-10-27 | 6 | 9 | 5.5 | 16 | 5 | 41.5
2017-10-29 | 3 | 6 | 3.5 | 16 | 5 | 33.5
2017-11-01 | 2 | 6 | 2.5 | 16 | 5 | 31.5
2017-11-03 | 2 | 6 | 2 | 16 | 5 | 31
2017-11-05 | 1 | 0 | 0 | 15 | 13 | 29
2017-11-08 | 1 | 0 | 0 | 15 | 6 | 22
2017-11-10 | 1 | 0 | 0 | 15 | 5 | 21
2017-11-12 | 1 | 0 | 0 | 12 | 5 | 18
2017-11-15 | 1 | 0 | 0 | 12 | 4 | 17
2017-11-16 | [5 empty] | 0
2017-11-18 | [5 empty] | 0
2017-11-20 | [5 empty] | 0
2017-11-22 | [5 empty] | 0
2017-11-24 | [5 empty] | 0
2017-11-26 | [5 empty] | 0
2017-11-28 | [5 empty] | 0